## Delivery Review
Green | Seamless Execution
Amber | Close Watch
Red | Needs Attention
Sr.no | Delivery Metrics |  | Axis Bank - Performance Audit & Optimisation (COE) | Axis Bank - Axis MF | Aditya Birla Finance Limited - Performance Testing | IDFC FIRST - Performance Audit & Optimisation (COE) | Rakuten - Performance Testing & Optimisation | Azentio - Audit & Optimisation | Ujjivan Finance - BR.Net Audit & Optimisation | Tata Capital - Performance Audit & Optimisation (COE) | Reliance - Reliance Retail | Reliance - Reliance New Commerce | Reliance - Reliance OSS/BSS | FSS - Performance Testing (COE) | Infosys - Income Tax - Performance Testing | IndusInd Bank - Performance Audit & Optimisation | Infosys - Icegate - Performance Testing | HDFC Bank - PAS - COE
| Area | Goal
1 | Project Brief |  | Running a Performance Management COE with focus on bringing business back to normal using SWAT activities and Improving QoS for applications with focus on improving P-A-S parameters. | Performance Audit and Optimisation for Customer Portal. | Performance Testing Project For Aditya Birla Finance | Running a Performance Management COE with focus on bringing business back to normal using SWAT activities and Improving QoS for applications with focus on improving P-A-S parameters. | There are two parallel tasks conducted : 1. Performance Testing and Optimisation for Key products. 2. Production troubleshooting through SWAT. | Performance assessment of the Lending application. The application is deployed at Emkan Finance where the customer has been having multiple issues. | Performance Audit and Optimisation for their BR.Net Application. | Running a Performance Management COE with focus on bringing business back to normal using SWAT activities and Improving QoS for applications with focus on improving P-A-S parameters. | Performance Testing and Automation testing for Reliance retail products. | Performance Testing for New Commerce products. | Performance engineering for Java applications during Performance testing. | Performance Testing and Engineering for POstability which is a POS application catering to Point of sale for merchants. This also involved building and scaling the SV. 1) The overall TPS was improved from 4 TPS to 383 TPS (avg) and 700 TPS (max). 2) The four stubs were scaled to 1000 TPS at 750 Concurrency. (This however could be achieved in 6 weeks time instead of 2 weeks ). | Performance Testing and Optimisation for the ITD platform. The extended project has been commenced with 13 people team. 9 people from Avekshaa and 4 people from Enhops. | Bringing down failure and bringing higher predictability across the business critical applications through four tracks : 1. Config Watcher Development and Implementation 2. Automated Code Review Toolkit Development and Implementation 3. Architecture Analysis of 8 Application 4. CIO Dashboards Creation of 8 Application 5. Performance Testing of 8 Application | Icegate Performance Testing Project from - Infosys | In HDFC Bank project we have to do SWAT Analysis, Audit & Optimization and Performance Testing.
2 | CSAT Details |  | Running a Performance Management COE with focus on bringing business back to normal using SWAT activities and Improving QoS for applications with focus on improving P-A-S parameters. | CSAT is submitted with client | WIP | Project feedback form has been shared with the customer and awaiting reponse. Follow ups are in process. Expected to get the CSAT by this week. Covered 8 applications in the last 20 weeks. There were 105 SWAT analysis for 8 application. Have successfully delivered all projects and have created further interest within teams. New application is getting onboarded every 3 weeks instead of 2 weeks because after IDFC FIRST wanted us to slow down the onboarding process to reduce the backlog. 100% recommendation is accepted by IDFC and respective OEM. Onboarding of new application on every after 2 weeks is positive feedback from client Positive feedback received from customer, and offer phase 2 for PE with 7 additonal application(8 is application is covered in 20 weeks) Overall status: Phase-2 PO is completed, and Phase-3 is in progress. | The project has come back to green now with the positive changes which has happened in the past one month. There was a joint review with Ashish, Rachit and Sanjay and then a feedback session with Rajinder, and Anurag has indicated that he has seen a positive impact. | WIP | WIP | Feedback is positive so far. Rachit had a discussion with Rajiv & Ashutosh & Bhavin. 8 applications have been on-boarded as a part of the monitoring stratgey. Quarter 1 is 3 application PE is closed, and have onboarded 3 more application for Quarter 2. 25+ SWAT analysis including finnone, Moneyfy user and PL&EMI application is complete. Ongoing status: Quarter 1 is completed, PO is recieved. | Feedback is +ve for delivery team. Request has been raised for a formal CSAT both by Ashish and Rachit, but yet to receive the same. However the client is happy and Nishu is also now settling into the project. | Formal CSAT needs to be collected. | Feedback is +ve for delivery team. Formal CSAT Feedback is not collected yet for this year. | Formal feedback yet to be received. | Currently the E-Filing has gone live and has multiple glitches. The CSAT will be taken at the end of the project. | No CSAT Received so far, Additionally carried out Performance Assessment for Connect Online and Miles and have covered COL under CW and ACRT and solved the production issue at Miles. Awaiting feedback on both apps. Achievements have been shared both with the Applications Heads and the CIO. | Project Started from 15th Sept. | This is the test
3 | % age of projects using P-A-S™ Assurance Tool Kit : |  | CSAT shared for 6 applications out of 10 completed. Avg rating, Overall Quality of Work : 7-10, Overall performance : Meets expectations Friendliness Quotient : Very friendly Willingness to re-engage/recommend : Definitely Project Objective : 90-120% Communication skills : 8-9 In constant pursuit of seeking for CSAT for other applications. | ACRT | PT on Cloud | 70% of time tool kit is used for performance audit and analysis. Dynatrace - 30%, log parsing/script - 20%, opentracing - 10%, Thread dump analyser/GC Analyser - 10%, Web assessment, baseline report - 30% (Manually + automated) | Not used in the project. | ACRT | ACRT New IIS Config Fetcher Tool is also created which will be tested and used in future projects. | AMT has been deployed on FinOne - Collection, mCollect and TCL-DMS. These applications are not covered under Dynatrace monitoring. | Not used currently in the project. | Not used currently in the project. | Not used currently in the project. | Not used in the project. | N.A. | Config Watcher, ACRT | We have built custom tool for building their 17 different file types extension files generation which will help us in generating bulk files for one of their use case. | This is the test
3 | % age customer reference-ability (new customers) |  | NA : Ongoing - Willing to speak for us. | N.A. | N.A. | Happy and can speak for us. | WIP. Can create opportunities in Rakuten Germany. | Have received a new opportunity on Performance testing and optimisation for a Wealth management system application & the proposal has been submitted. This will be run in a TnM model. | N.A. | Happy and can speak for us. | Happy and can speak for us. | Happy and can speak for us. | Happy and can speak for us. | N.A. | Have received a new opportunity on IceGate. Project to commence from 15th Sep. | N.A. | NA | This is the test
4 | % age project artifacts submitted to AveKen/Techninja |  | All reports are copied in one central location of Google Drive | WIP | WIP | Recommendation tracker submitted to Client. Recommendation tracker have been convered into Techninja format, under review of Project lead | Need to be shared. | Need to be shared. | We are modifying our current tracker with more features and PMP will hold all trackers in future | Recommendation tracker submitted to Client. Recommendation tracker have been convered into Techninja format, under review of Project lead | Submitted to the product team. | Submitted to the product team. | Need to be shared. | Shared with Babu. | Submitted to Techninja. Latest tracker needs to be updated. | 1. ACRT - Code is in github 2. Config Watcher - Code is in github | WIP | This is the test
5 | Qualilty artifacts submitted to AveKen/Techninja |  | On-going. | WIP | WIP | Recommendation tracker is reviewed and maintained in as per standard required by Aveken Techninja | Need to be shared. | WIP | WIP | Recommendation tracker is reviewed and maintained in as per standard required by Aveken Techninja. | Done | Done | N.A. | Shared with Babu. | Shared till 1 month back. | On-going. | WIP | This is the test
6 | % age repeat business (downstream) from new clients (measured by the value of repeat business vs initial) |  | The renewal is under progress. The ROI was established with the senior management using sample applications and with the procurement team. This was very well appreciated. | This is business got from Axis Bank Reference | This is repeat business of earlier done project | Phase 2 of the project is in progress and we have received the PO for the same. | N.A. | WIP | N.A. | Quarter 2 is started based on Quarter 1 report verbal feedback. | N.A. | N.A. | N.A. | N.A. | 1) Project has got extended till Dec. 21. 2) Have received a new opportunity on IceGate and the project will commence from 15th Sep. | N.A. | NA | This is the test
7 | Outcome based project |  | N.A. | N.A. | WIP | Phase 1 - 100% success. | TnM | N.A. | N.A. | N.A. | T&M | T&M | T&M | N.A. | Project has moved from FP to TnM since July 2021. | 100% - 81% amount billed. Plan in place to bill the rest of 19%. | NA | This is the test
8 | Deliver FP projects with-in the planned budgeted efforts |  | 100% | 100% | 100% | N.A. | TnM | N.A. | 100% | N.A. | N.A. | N.A. | N.A. | Delayed by 2 months. However team was deployed into another projects. | Project has got extended. Delivery has already started in a TnM model. | 100% | YES | This is the test
9 | Role ratio(target Vs Actuals) -Reduce the costing of each offerings |  | 60:20:20 | 66:33:0 | 33:0:66 | 33:0:66 | 33:33:33 | 0:0:0 | 60:20:20 | 25:33:41 | 25:12:62 | 66:33:0 | 50:50:0 | 20:20:60 | 23:30:46 | 66:33:0 | 9:27:63 | 0:0:0
10 | Cost Reduction / improve profitability through automation |  | As a part of the automation, we are leveraging ACRT and System Tracer and Bulk AWR Parser Tools. | ACRT is being used for Code Review Activities. | First actual implementation of PT on Cloud. Additional revenue with Microfocus VUH product. | Vinayak, Ganesh and Mayuri is 100% billable in phase-1. In order to improve profitability, the plan to train Ganesh and Ved to manage phase-2 independently have been accomplished, and 80% of project time is utilized by Vinayak for another project. .Next plan is to train junior folks to take over senior people's task, and Ved, Ganesh will be involved in running the program, and will be available for another project as a consultant with 50% of ratio. Ganesh (STA) and Sajid (SSE) is now sharable in IDFC, &TCL Project . Ved also will be involved in another project after 6 months of time. The future plan is to run IDFC project with Ved (sharable), Ganesh(Sharable), Meenkashi(100%), Manish(100%), Mayuri(Sharable), Sajid(Sharable) was planned to be sharable starting from Oct 2021 which have started from 3rd week of Aug. Vinayak is running the execution, handling esclation and performaing account head role. Billing role higher than actual role. | N.A. | Actual effort was 53% lesser than planned effort ( 192 man days effort planned vs 102 man days effort spent). | ACRT is being used for Code Review Activities | 1) Vinayak has enabled Smita (STS) to work on daily schedules and Vinayak only gets involved during SWAT activities. Billed role is 1 STA, 1 STS, 3 SSE. Actual Role is 1 TA, 1 TS, 3 SSE. Building role higher than actual role. Trained the SE to perform SSE/TS role, now can perform basic activities like baseline report, web assessement report, ELK, Shell scripting. 2) AMT will provide us further stickiness into the account. Without any conflict with DT. | N.A. | N.A. | N.A. | N.A. | This has moved from 33:23:44 to 35:29:35 | Config Watcher is built from scratch and the ACRT Tool, there are more tools in progress. | Yes majorly junior resources are onboarded in this project. | This is the test
11 | Ensure no risk in the project |  | The performance and reliability issues are chronic and needs deep expertise to solve. The team needs constant support from leadership team for support. Axis Bank team has introduced some internal team members and have asked our team to involve them during analysis. We have objected to this. | No Risk. | No Risk | In total 400+ recommendations were provided for 8 application including phase1 and 2, the recommendation were provided across architecture, frontend, configuration, database, Monitoring strategies, SWAT Analysis etc. The road map for the implementation of Recommendations have been discussed and categorized in long/short/medium term. IDFC FIRST is slow in implementing the recommendation, Avekshaa team is following up with various project team since form week9, but still slowness is observed. A fast track team is set up to follow up with IDFC team, and shared the Recommendation report with 3 category viz. system at risk, potential risk and best practices (with detailed summary report in PPT). Follow up with customer and as per IDFC SPOC, Avekshaa team have done correct job, Project team is not respnding due to other priorities. So we have submitted the report of Phase 1 and Phase 2 to Surajit and Devendra. The steering committe is appointed for the same Do not see any risk | Currently no risk in the project. 1. Introduction of CAKD expert. 2. Building skills on Network analysis within the team. 3. Introduction of a smart SSE with experience on PT and ELK stack. | Response from end client is very slow. Escalation made. Steering Committee Meeting is conducted every week. Meeting conducted with IT Head of Emkaan and all points were raised with him. The need for having an NDA with Avekshaa was raised. Azentio is handling that situation. At Emkaan, it is being iternally discussed, the access that will be raised for Avekshaa. Rachit has asked Sudipto to raise all invoices. We will support Azentio after getting the requsite access. | No Risk | In previous quarter, we were getting slow responses from application owners for the new set of applications which have been onboarded. The same has been discussed with Mehjabeen Aalam, Vijay Kadam, Pramod Nair and will be facilitated. Now Avekshaa team is getting quicker response, and have onboarded total 5 application for this quarter. SWAT Analysis shared with TCL and 50% recommendation implemented, consistent follow up is going on. 5 Prod showstoppers, 28 Major and 1 was minor SWAT analysis delivered with 0% esclation rate. Do no see any risk. | Nishu has replaced Ashish and is settling down. Naveen has also put down his papers, however the overlap has already begun with Manoj who is a smart talent and has worked with Nishu in previous project (so there is compatibility). | No Risk. | No Risk. | Customer has not acknowledged the delivery of the SV as it was outside the delivery timeline. There was a meeting called out to find a solution to move forward, however the team is not looking for the SV code anymore. | Currently aligned to the 25th Oct plan. However, there are other features which will be developed in due course of time. Currently out of 32 uses cases 22 are successfully passed and 4 are in review stage and 6 are currently failing due to application issues. | There is a risk with this client as no one to support activities at ground level. | There is not Risk in the project but access is taking time from client side. As per latest update we will get access early next week. | NA
12 | Innovation / Best practices - created and implemented across the Organization |  | System Tracer Utility and Bulk AWR Parser Tools were developed in this project which can be used in other projects. | Yes Kubernetes related analysis document creation is in progress. | VUH Model Usage Documentation Created which can be used in future PT Projects where HPLR VUH is used. | New applications will get added from next phase, so learning from previous application will be implemented in next phase Maintain daily NFR document for NEO application which can be reused in any application baseline. Unified dashboard is created in Dynatrace for getting more insight. Baseline report have been streamline, and have trainned the people to complete in 1 week which was earlier used to complete in 3 weeks of times. Got appreciation from Surajit, CTO of IDFC Bank for dashboard created for MDM application. | N.A. | ACRT utilised for Automated Code review. | WIP | Plan to integrate Sniper - in progress. | N.A. | N.A. | N.A. | SV created which was cumbersome and this can be resued for any application which is interacting with the payment switch. | HPLR Cloud Solution is given to Infosys and that is accepted and purchased 30Lacs VUH and its deployment is also completed. | PMP Platform is Created which can be used across clients and also ACRT Tool is developed. | NA | NA
13 | Revenue leakage |  | No revenue leakage. | No Revenue Leakage. | WIP | No revenue leakage. | No revenue leakage. | N.A. | WIP | No revenue leakage. | No revenue leakage. | Rahul has replaced Abhiraj, received the approval and will be onboarded in System by 16 July. The onboarding for Aman's replacement is in progress. | No revenue leakage. | 1. Delayed by 2 months. 2. SV Effort is more than budgeted. | No revenue leakage. | 81% payment is received. Plan in place to work on the rest 19% with minimum effort. | 13 Payment issue is resolved by Sanjay and it will be accommodated in future invoices. | NA
14 | Employee Satisfaction |  | Stretched working hours, complex scenarios, mental anxiety within team members. | No Issues in terms of employee satisfaction. | No Issues in terms of employee satisfaction. | Happy team :) | No issues. | N.A. | No Issues in terms of employee satisfaction | Happy team :) | No Issue. | No Issue. | No Issue. | Digvijay was not transparent with the progress of the development and provided wrong information. This was one major reason why we had to disassociate him from the organisation. | Need to plan to create an incentive model for additional days working. Have proposed to the team that if they create 1.5 days billing for themselves, the additional revenue generated will be shared with the team members. | No Issues in terms of employee satisfaction. | All employees are satisfied in project | NA
[16 empty] | 15 |  |  | 1. Team should be equipped with good set of paid vs inhouse tools for better quality of deliveries 2. Knowledge of team should be enhanced on different time intervals 3. Showcasing data to senior stakeholders on different time intervals is required. 4. Creating a business benefit chart for all the concluded projects and sharing the same with the senior management on periodic basis. | 1. Good team should be deployed in new accounts 2. We should not be using the same blended rate as of a Performance management solution. | N.A. | 1) SAAS cloud migration(platform development) 2) Build higher roles in the team, time management skills in teams, Create champions and Build Good Teams. Junior folks are trainned to take the day to day task without supervisor help, and Senior people will be involved in running the project, and involving in another project as a consultant with 50% of ratio. 3) Few senior people were new, and was required time to upskills themself, hence wasn't able take out the junior people for another project So we have trainnned the TS and now Sajid & Mayuri can work as sharable talent in other FP Project. 4) There is scope of quality of work, the approach to cover validation, verification, precision, accuracy. | Staffing opportunities has complexities. As these are gated projects, the support provided from outside team is limited. Hence, good resources needs to be deployed in these projects and rates needs to be negotiated accordingly. | N.A. | N.A. | 1) SAAS cloud migration(platform development) 2) Build higher roles in the team, time management skills in teams, Create champions and Build Good Teams. Junior folks are trainned to take the day to day task without supervisor help, and Senior people will be involved in running the project, and involving in another project as a consultant with 50% of ratio. 3) There is scope of quality of work, the approach to cover validation, verification, precision, accuracy. | On-Boarding and off-boarding in Reliance is a very tedious process. Hence, we should carry out a cultural fitment assessment followed by customer onboarding induction to ensure the team member is fully equipped with the customer and its ways of working. | Database Architect is not the correct selection for leading PT based project. | Running with one person who has been in the system for long. It’s a person dependant project. Need to see that Ramakant is not poached by Reliance. | 1. SV Deliverables are difficult to meet and can be complex. While this was picked up as the deal would not have come through, it has led to challenges in the deliverables. We should not attempt to pick up SV development unless it is completely known and paid for. 2. The seniors should have come on-boarded quickly and should have addressed the issue. 3. Rachit could have done a communication with the client earlier than he normally did to understand their frustration. 4. We should be selective in working with organisations looking at the credit worthiness and the people involved in the project. | Complex programs need strong leader who is both committed and technically extremely sound. Working with IT companies, we will have to be more prepared before we get into these programs. | 1. We should only involve in project execution when required data is received 2. Handling Multiple Stakholders is not easy task so separate Project Manager- Technical is required to manage such a large project 3. Team evaluation is necessary before starting such a large program 4. Internal team training is required before executing this type of large programs 5. Development and Audit projects should not be clubbed together as both has different way of executions. 6. Regular governance calls are required in large programs with 3-4 senior resources from Avekshaa. | 1. We should always start work after receiving the PO and after client sent mail to kick start work and we should not hurry in starting the project without PO or on verbal communication. | NA

## Current Deployment
Sr.No | Consultant Name | Role | Current Status | Last Working Date | 05/04/2021 | 12/04/2021 | 19/04/2021 | 26/04/2021 | 03/05/2021 | 10/05/2021 | 17/05/2021 | 24/05/2021 | 31/05/2021 | 07/06/2021 | 14/06/2021 | 21/06/2021 | 28/06/2021 | 05/07/2021 | 12/07/2021 | 19/07/2021 | 26/07/2021 | 02/08/2021 | 09/08/2021 | 16/08/2021 | 23/08/2021 | 30/08/2021 | 06/09/2021 | 13/09/2021 | 20/09/2021 | 27/09/2021 | 04/10/2021 | 11/10/2021 | 18/10/2021 | 25/10/2021 | 01/11/2021 | 08/11/2021 | 15/11/2021 | 22/11/2021 | 29/11/2021 | 06/12/2021 | 13/12/2021 | 20/12/2021 | 27/12/2021 | 03/01/2022 | 10/01/2022 | 17/01/2022 | 24/01/2022 | 31/01/2022 | 07/02/2022 | 14/02/2022 | 21/02/2022 | 28/02/2022 | 07/03/2022 | 14/03/2022 | 21/03/2022 | 28/03/2022
Section A : Active Consultants | Section A : Active Consultants | Section A : Active Consultants | Section A : Active Consultants | Section A : Active Consultants | Section A : Active Consultants | Section A : Active Consultants | Section A : Active Consultants | Section A : Active Consultants | Section A : Active Consultants | Section A : Active Consultants | Section A : Active Consultants | Section A : Active Consultants | Section A : Active Consultants | Section A : Active Consultants | Section A : Active Consultants | Section A : Active Consultants | Section A : Active Consultants | Section A : Active Consultants | Section A : Active Consultants | Section A : Active Consultants | Section A : Active Consultants | Section A : Active Consultants | Section A : Active Consultants | Section A : Active Consultants | Section A : Active Consultants | Section A : Active Consultants | Section A : Active Consultants | Section A : Active Consultants | Section A : Active Consultants | Section A : Active Consultants | Section A : Active Consultants | Section A : Active Consultants | Section A : Active Consultants | Section A : Active Consultants | Section A : Active Consultants | Section A : Active Consultants | Section A : Active Consultants | Section A : Active Consultants | Section A : Active Consultants | Section A : Active Consultants | Section A : Active Consultants | Section A : Active Consultants | Section A : Active Consultants | Section A : Active Consultants | Section A : Active Consultants | Section A : Active Consultants | Section A : Active Consultants | Section A : Active Consultants | Section A : Active Consultants | Section A : Active Consultants | Section A : Active Consultants | Section A : Active Consultants | Section A : Active Consultants | Section A : Active Consultants | Section A : Active Consultants
1 | Ram Singh | Associate Principal Architect | Partially Billed | Still in Organization | IndusInd Bank | IndusInd Bank | IndusInd Bank | IndusInd Bank | IndusInd Bank | IndusInd Bank | IndusInd Bank | IndusInd Bank | IndusInd Bank | IndusInd Bank | IndusInd Bank | IndusInd Bank | IndusInd Bank | IndusInd Bank | Ujjivan Finance, IndusInd Bank | Ujjivan Finance, IndusInd Bank | Ujjivan Finance, IndusInd Bank | Ujjivan Finance, IndusInd Bank | Ujjivan Finance, IndusInd Bank | Ujjivan Finance, IndusInd Bank | Ujjivan Finance, IndusInd Bank | Ujjivan Finance, IndusInd Bank | Axis Bank, Infosys, IndusInd Bank | Axis Bank, Infosys, IndusInd Bank | Axis Bank, Infosys, IndusInd Bank | Axis Bank, Infosys, IndusInd Bank | Axis Bank, Infosys, Infosys, IndusInd Bank | Axis Bank, Infosys, Infosys, IndusInd Bank | Axis Bank, Infosys, Infosys, IndusInd Bank | Axis Bank, Infosys, Infosys, IndusInd Bank | Axis Bank, Infosys, Infosys, IndusInd Bank | Axis Bank, Infosys, Infosys | Axis Bank, Infosys, Infosys | Axis Bank, Infosys, Infosys | Axis Bank, Infosys, Infosys | Axis Bank, Infosys, Infosys | Axis Bank, Infosys, Infosys | Axis Bank, Infosys | Axis Bank, Infosys | Axis Bank | Axis Bank | Axis Bank | Axis Bank | Axis Bank | Axis Bank | Axis Bank | Axis Bank | Axis Bank | Axis Bank | Axis Bank | Axis Bank | Axis Bank
2 | Bhavin Chedda | Technical Architect | Billable | Still in Organization | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Axis Bank | Axis Bank | Axis Bank | Axis Bank | Ujjivan Finance | Ujjivan Finance | Ujjivan Finance | Ujjivan Finance | Ujjivan Finance | Ujjivan Finance | Ujjivan Finance | Ujjivan Finance | HDFC Bank, Ujjivan Finance | HDFC Bank, Ujjivan Finance | HDFC Bank | HDFC Bank | HDFC Bank | HDFC Bank | HDFC Bank | HDFC Bank | HDFC Bank | HDFC Bank | HDFC Bank | HDFC Bank | HDFC Bank | HDFC Bank | HDFC Bank | HDFC Bank | HDFC Bank | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench
3 | Akash Kumar Sahu | Technical Specialist | Billable | Still in Organization | [18 empty] | Ujjivan Finance | Ujjivan Finance | Ujjivan Finance | Ujjivan Finance | Ujjivan Finance | Ujjivan Finance | Ujjivan Finance | Bench | Bench | Bench | Bench | Bench | Axis Bank | Axis Bank | Axis Bank | Axis Bank | Axis Bank | Axis Bank | Axis Bank | Axis Bank | Axis Bank | Axis Bank | Axis Bank | Axis Bank | Axis Bank | Axis Bank | Axis Bank | Axis Bank | Axis Bank | Axis Bank | Axis Bank | Axis Bank | Axis Bank | Axis Bank
4 | Digendra Singh | Senior Technical Architect | Billable | Still in Organization | [23 empty] | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench
5 | Mahesh Khairnar | Senior Technical Architect | Bench | Still in Organization | Axis Bank | Axis Bank | Axis Bank | Axis Bank | Axis Bank | Axis Bank | Axis Bank | Axis Bank | Axis Bank | Axis Bank | Axis Bank | Axis Bank | Axis Bank | Axis Bank | Axis Bank | Axis Bank | Axis Bank | Axis Bank | Axis Bank | Axis Bank | Axis Bank | Axis Bank | Axis Bank | Axis Bank | Axis Bank | Axis Bank | Axis Bank | Axis Bank | Axis Bank | Axis Bank | Axis Bank | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench
6 | Shubham More | Software Engineer | Bench | Still in Organization | Axis Bank | Axis Bank | Axis Bank | Axis Bank | Axis Bank | Axis Bank | Axis Bank | Axis Bank | Axis Bank | Axis Bank | Axis Bank | Axis Bank | Axis Bank | Axis Bank | Axis Bank | Axis Bank | Axis Bank | Axis Bank | Axis Bank | Axis Bank | Axis Bank | Axis Bank | Axis Bank | Axis Bank | Axis Bank | Axis Bank | Axis Bank | Axis Bank | Axis Bank | Axis Bank | Axis Bank | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench
7 | Parul Jain | Technical Architect | Bench | Still in Organization | Axis Bank | Axis Bank | Axis Bank | Axis Bank | Axis Bank | Axis Bank | Axis Bank | Axis Bank | Axis Bank | Axis Bank | Axis Bank | Axis Bank | Axis Bank | Axis Bank | Axis Bank | Axis Bank | Axis Bank | Axis Bank | Axis Bank | Axis Bank | Axis Bank | Axis Bank | Axis Bank | Axis Bank | Axis Bank | Axis Bank | Axis Bank | Axis Bank | Axis Bank | Axis Bank | Axis Bank | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench
8 | Sweta Varshney | Technical Architect | Bench | Still in Organization | Axis Bank | Axis Bank | Axis Bank | Axis Bank | Axis Bank | Axis Bank | Axis Bank | Axis Bank | Axis Bank | Axis Bank | Axis Bank | Axis Bank | Axis Bank | Axis Bank | Axis Bank | Axis Bank | Axis Bank | Axis Bank | Axis Bank | Axis Bank | Axis Bank | Axis Bank | Axis Bank | Axis Bank | Axis Bank | Axis Bank | Axis Bank | Axis Bank | Axis Bank | Axis Bank | Axis Bank | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench
9 | Ved Bhure | Technical Architect | Bench | Still in Organization |  | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench
10 | Manoj Kumar Sankella | Senior Software Engineer | Bench | Still in Organization | FSS | FSS | FSS | FSS | FSS | FSS | FSS | FSS | FSS | Aditya Birla Finance Limited | Aditya Birla Finance Limited | Aditya Birla Finance Limited | Aditya Birla Finance Limited | Aditya Birla Finance Limited | Aditya Birla Finance Limited | Aditya Birla Finance Limited | Aditya Birla Finance Limited | Bench | Bench | Bench | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench
11 | Pranali Shirodkar | Software Engineer | Bench | Still in Organization | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Aditya Birla Finance Limited | Aditya Birla Finance Limited | Aditya Birla Finance Limited | Aditya Birla Finance Limited | Aditya Birla Finance Limited | Aditya Birla Finance Limited | Aditya Birla Finance Limited | Aditya Birla Finance Limited | Bench | Bench | Bench | Bench | Bench | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench
12 | Vinayak Shinde | Associate Principal Architect | Bench | Still in Organization | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench
13 | Mayuri Khokrale | Software Engineer | Bench | Still in Organization | IDFC FIRST | IDFC FIRST | IDFC FIRST | IDFC FIRST | IDFC FIRST | IDFC FIRST | IDFC FIRST | IDFC FIRST | IDFC FIRST | IDFC FIRST | IDFC FIRST | IDFC FIRST | IDFC FIRST | IDFC FIRST | IDFC FIRST | IDFC FIRST | IDFC FIRST | IDFC FIRST | IDFC FIRST | IDFC FIRST | IDFC FIRST | IDFC FIRST | IDFC FIRST | IDFC FIRST | IDFC FIRST | IDFC FIRST | IDFC FIRST | IDFC FIRST | IDFC FIRST | IDFC FIRST | IDFC FIRST | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench
14 | MD Sajid | Software Engineer | Bench | Still in Organization | Tata Capital, IDFC FIRST | IDFC FIRST | IDFC FIRST | IDFC FIRST | IDFC FIRST | IDFC FIRST | IDFC FIRST | IDFC FIRST | IDFC FIRST | IDFC FIRST | IDFC FIRST | IDFC FIRST | IDFC FIRST | IDFC FIRST | IDFC FIRST | IDFC FIRST | IDFC FIRST | IDFC FIRST | IDFC FIRST | IDFC FIRST | IDFC FIRST | IDFC FIRST | IDFC FIRST | IDFC FIRST | IDFC FIRST | IDFC FIRST | IDFC FIRST | IDFC FIRST | IDFC FIRST | IDFC FIRST | IDFC FIRST | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench
15 | Ganesh T Shenai | Technical Architect | Bench | Still in Organization | IDFC FIRST | IDFC FIRST | IDFC FIRST | IDFC FIRST | IDFC FIRST | IDFC FIRST | IDFC FIRST | IDFC FIRST | IDFC FIRST | IDFC FIRST | IDFC FIRST | IDFC FIRST | IDFC FIRST | IDFC FIRST | IDFC FIRST | IDFC FIRST | IDFC FIRST | IDFC FIRST | IDFC FIRST | IDFC FIRST | IDFC FIRST | IDFC FIRST | IDFC FIRST | IDFC FIRST | IDFC FIRST | IDFC FIRST | IDFC FIRST | IDFC FIRST | IDFC FIRST | IDFC FIRST | IDFC FIRST | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench
16 | Ramakant Ingole | Senior Technical Specialist | Bench | Still in Organization | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench
17 | Ashish Modi | Associate Principal Architect | Bench | Still in Organization | FSS, Reliance, Reliance, Reliance | FSS, Reliance, Reliance, Reliance | FSS, Reliance, Reliance, Reliance | FSS, Reliance, Reliance, Reliance | FSS, Reliance, Reliance, Reliance | FSS, Reliance, Reliance, Reliance | FSS, Reliance, Reliance, Reliance | FSS, Reliance, Reliance, Reliance | FSS, Reliance, Reliance, Reliance | FSS, Reliance, Reliance, Reliance | FSS, Reliance, Reliance, Reliance | FSS, Reliance, Reliance, Reliance | FSS, Reliance, Reliance, Reliance | Reliance, Reliance, Reliance | Reliance, Reliance, Reliance, Rakuten | Reliance, Reliance, Reliance, Rakuten | Reliance, Reliance, Reliance, Rakuten | Reliance, Reliance, Reliance, Rakuten | Reliance, Reliance, Reliance, Rakuten | Reliance, Reliance, Reliance, Rakuten | Reliance, Reliance, Reliance, Rakuten | Reliance, Reliance, Reliance, Rakuten | Reliance, Reliance, Reliance, Rakuten | Reliance, Reliance, Reliance, Rakuten | Reliance, Reliance, Reliance, Rakuten | Reliance, Reliance, Reliance, Rakuten | Reliance, Reliance, Reliance, Rakuten | Reliance, Reliance, Reliance, Rakuten | Reliance, Reliance, Reliance, Rakuten | Reliance, Reliance, Reliance, Rakuten | Reliance, Reliance, Reliance, Rakuten | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench
18 | Prabhakar Madipelly | Technical Specialist | Bench | Still in Organization | Rakuten | Rakuten | Rakuten | Rakuten | Rakuten | Rakuten | Rakuten | Rakuten | Rakuten | Rakuten | Rakuten | Rakuten | Rakuten | Rakuten | Rakuten | Rakuten | Rakuten | Rakuten | Rakuten | Rakuten | Rakuten | Rakuten | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench
19 | Nikhil Bhise | Technical Architect | Bench | Still in Organization | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Rakuten | Rakuten | Rakuten | Rakuten | Rakuten | Rakuten | Rakuten | Rakuten | Rakuten | Rakuten | Rakuten | Rakuten | Rakuten | Rakuten | Rakuten | Rakuten | Rakuten | Rakuten | Rakuten | Rakuten | Rakuten | Rakuten | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench
20 | Puttur Jayachandra | Technical Specialist | Bench | Still in Organization | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench
21 | Aman Kumar | Technical Specialist | Bench | Still in Organization | Rakuten | Rakuten | Rakuten | Rakuten | Rakuten | Rakuten | Rakuten | Rakuten | Rakuten | Rakuten | Rakuten | Rakuten | Rakuten | Rakuten | Rakuten | Rakuten | Rakuten | Rakuten | Rakuten | Rakuten | Rakuten | Rakuten | Rakuten | Rakuten | Rakuten | Rakuten | Rakuten | Rakuten | Rakuten | Rakuten | Rakuten | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench
22 | Naveen Kumar | Technical Specialist | Bench | Still in Organization | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench
23 | Abhiraj Salvi | Technical Architect | Bench | Still in Organization | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Ujjivan Finance, Azentio | Ujjivan Finance, Azentio | Ujjivan Finance, Azentio | Ujjivan Finance, Azentio | Ujjivan Finance, Azentio | Ujjivan Finance, Azentio | Ujjivan Finance, Azentio | Ujjivan Finance, Azentio | Ujjivan Finance, Azentio | Ujjivan Finance, Azentio | Ujjivan Finance, Azentio | Ujjivan Finance, Azentio | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench
24 | Ajay Jha | Technical Specialist | Bench | Still in Organization | Rakuten | Rakuten | Rakuten | Rakuten | Rakuten | Rakuten | Rakuten | Rakuten | Rakuten | Rakuten | Rakuten | Rakuten | Rakuten | Rakuten | Rakuten | Rakuten | Rakuten | Rakuten | Rakuten | Rakuten | Rakuten | Rakuten | Rakuten | Rakuten | Rakuten | Rakuten | Rakuten | Rakuten | Rakuten | Rakuten | Rakuten | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench
25 | Saurabh Jha | Software Engineer | Bench | Still in Organization | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench
26 | Mahesh Madbul | Technical Specialist | Bench | Still in Organization | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Bench | Bench | Bench | Bench | Bench | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench
27 | Smita Changdev | Technical Architect | Bench | Still in Organization | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench
28 | Ramesh Khalindi | Technical Architect | Bench | Still in Organization | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench
29 | Ganesan M | Software Engineer | Bench | Still in Organization | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Ujjivan Finance | Ujjivan Finance | Ujjivan Finance | Ujjivan Finance | Ujjivan Finance | Ujjivan Finance | Ujjivan Finance | Ujjivan Finance | Ujjivan Finance | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench
30 | Chandan K S | Software Engineer | Bench | Still in Organization | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench
31 | Omkar Narvekar | Software Engineer | Bench | Still in Organization | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench
32 | Omkar Madhukar Gitaye | Software Engineer | Bench | Still in Organization | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench
33 | Apoorva Singh | Software Engineer | Bench | Still in Organization | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench
34 | Vinayak Gupta | Software Engineer | Bench | Still in Organization | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench
35 | Anita Rajesh Maurya | Software Engineer | Bench | Still in Organization | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench
36 | Pranit Pramod Bandkar | Software Engineer | Bench | Still in Organization | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench
37 | Mandar Pradeep Salunkhe | Software Engineer | Bench | Still in Organization | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench
38 | Anita Shivaji khade | Software Engineer | Bench | Still in Organization | FSS | FSS | FSS | FSS | FSS | FSS | FSS | FSS | FSS | FSS | FSS | FSS | FSS | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench
39 | Abhilash Korutla | Technical Specialist | Bench | Still in Organization | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench
40 | Josiphiah K | Senior Software Engineer | Bench | Still in Organization | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench
41 | Manish Sarang | Technical Specialist | Bench | Still in Organization |  |  | Bench | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench
42 | Meenakshi Chaliha | Technical Specialist | Bench | Still in Organization |  | Bench | Bench | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench
43 | Bhaskar Naidu K | Senior Software Engineer | Bench | Still in Organization | Bench | Bench | Bench | Bench | Rakuten | Rakuten | Rakuten | Rakuten | Rakuten | Rakuten | Rakuten | Rakuten | Rakuten | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench
44 | Manjunadh Reddy | Senior Software Engineer | Bench | Still in Organization | Bench | Bench | Bench | Bench | Rakuten | Rakuten | Rakuten | Rakuten | Rakuten | Rakuten | Rakuten | Rakuten | Rakuten | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench
45 | Rishi Ranjan | Associate Principal Architect | Bench | Still in Organization | [10 empty] | Bench | Bench | Bench | Azentio | Azentio | Azentio | Azentio | Azentio | Azentio | Azentio | Azentio | Azentio | Azentio | Azentio | Azentio | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench
46 | Siddhesh Jadhav | Technical Specialist | Bench | Still in Organization | [17 empty] | Bench | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench
47 | Sangita Chavan | Technical Specialist | Bench | Still in Organization | [18 empty] | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Tata Capital | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench
Section B : Employee who has left this organisation in this period | Section B : Employee who has left this organisation in this period | Section B : Employee who has left this organisation in this period | Section B : Employee who has left this organisation in this period | Section B : Employee who has left this organisation in this period | Section B : Employee who has left this organisation in this period | Section B : Employee who has left this organisation in this period | Section B : Employee who has left this organisation in this period | Section B : Employee who has left this organisation in this period | Section B : Employee who has left this organisation in this period | Section B : Employee who has left this organisation in this period | Section B : Employee who has left this organisation in this period | Section B : Employee who has left this organisation in this period | Section B : Employee who has left this organisation in this period | Section B : Employee who has left this organisation in this period | Section B : Employee who has left this organisation in this period | Section B : Employee who has left this organisation in this period | Section B : Employee who has left this organisation in this period | Section B : Employee who has left this organisation in this period | Section B : Employee who has left this organisation in this period | Section B : Employee who has left this organisation in this period | Section B : Employee who has left this organisation in this period | Section B : Employee who has left this organisation in this period | Section B : Employee who has left this organisation in this period | Section B : Employee who has left this organisation in this period | Section B : Employee who has left this organisation in this period | Section B : Employee who has left this organisation in this period | Section B : Employee who has left this organisation in this period | Section B : Employee who has left this organisation in this period | Section B : Employee who has left this organisation in this period | Section B : Employee who has left this organisation in this period | Section B : Employee who has left this organisation in this period | Section B : Employee who has left this organisation in this period | Section B : Employee who has left this organisation in this period | Section B : Employee who has left this organisation in this period | Section B : Employee who has left this organisation in this period | Section B : Employee who has left this organisation in this period | Section B : Employee who has left this organisation in this period | Section B : Employee who has left this organisation in this period | Section B : Employee who has left this organisation in this period | Section B : Employee who has left this organisation in this period | Section B : Employee who has left this organisation in this period | Section B : Employee who has left this organisation in this period | Section B : Employee who has left this organisation in this period | Section B : Employee who has left this organisation in this period | Section B : Employee who has left this organisation in this period | Section B : Employee who has left this organisation in this period | Section B : Employee who has left this organisation in this period | Section B : Employee who has left this organisation in this period | Section B : Employee who has left this organisation in this period | Section B : Employee who has left this organisation in this period | Section B : Employee who has left this organisation in this period | Section B : Employee who has left this organisation in this period | Section B : Employee who has left this organisation in this period | Section B : Employee who has left this organisation in this period | Section B : Employee who has left this organisation in this period
48 | Ajay Jhaveri | Senior Technical Specialist | Billable | Still in Organization | IndusInd Bank | IndusInd Bank | IndusInd Bank | IndusInd Bank | IndusInd Bank | Axis Bank | Axis Bank | Axis Bank | Axis Bank | Axis Bank, Axis Bank | Axis Bank, Axis Bank | Axis Bank, Axis Bank | Axis Bank, Axis Bank | Axis Bank, Axis Bank | Axis Bank, Axis Bank | Axis Bank | Axis Bank | Axis Bank | Axis Bank | Axis Bank | Axis Bank | Axis Bank | Axis Bank | Axis Bank | Axis Bank | Axis Bank | Axis Bank | Axis Bank | Axis Bank | Axis Bank | Axis Bank
49 | Nishu BG | Technical Architect | Billable | Still in Organization | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance
50 | Vamsi Krishna Guntupalli | Technical Architect | Billable | Still in Organization | Rakuten | Rakuten | Rakuten | Rakuten | Rakuten | Rakuten | Rakuten | Rakuten | Rakuten | Rakuten | Rakuten | Rakuten | Rakuten | Rakuten | Rakuten | Rakuten
51 | Vijayshree Tumaram Shinde | Senior Software Engineer | Billable | Still in Organization | Rakuten | Rakuten | Rakuten | Rakuten | Rakuten | Rakuten | Rakuten | Rakuten | Rakuten | Rakuten | Rakuten | Rakuten | Rakuten | Rakuten | Rakuten | Rakuten
Section C : Partner EcoSystem | Section C : Partner EcoSystem | Section C : Partner EcoSystem | Section C : Partner EcoSystem | Section C : Partner EcoSystem | Section C : Partner EcoSystem | Section C : Partner EcoSystem | Section C : Partner EcoSystem | Section C : Partner EcoSystem | Section C : Partner EcoSystem | Section C : Partner EcoSystem | Section C : Partner EcoSystem | Section C : Partner EcoSystem | Section C : Partner EcoSystem | Section C : Partner EcoSystem | Section C : Partner EcoSystem | Section C : Partner EcoSystem | Section C : Partner EcoSystem | Section C : Partner EcoSystem | Section C : Partner EcoSystem | Section C : Partner EcoSystem | Section C : Partner EcoSystem | Section C : Partner EcoSystem | Section C : Partner EcoSystem | Section C : Partner EcoSystem | Section C : Partner EcoSystem | Section C : Partner EcoSystem | Section C : Partner EcoSystem | Section C : Partner EcoSystem | Section C : Partner EcoSystem | Section C : Partner EcoSystem | Section C : Partner EcoSystem | Section C : Partner EcoSystem | Section C : Partner EcoSystem | Section C : Partner EcoSystem | Section C : Partner EcoSystem | Section C : Partner EcoSystem | Section C : Partner EcoSystem | Section C : Partner EcoSystem | Section C : Partner EcoSystem | Section C : Partner EcoSystem | Section C : Partner EcoSystem | Section C : Partner EcoSystem | Section C : Partner EcoSystem | Section C : Partner EcoSystem | Section C : Partner EcoSystem | Section C : Partner EcoSystem | Section C : Partner EcoSystem | Section C : Partner EcoSystem | Section C : Partner EcoSystem | Section C : Partner EcoSystem | Section C : Partner EcoSystem | Section C : Partner EcoSystem | Section C : Partner EcoSystem | Section C : Partner EcoSystem | Section C : Partner EcoSystem
52 | Mahendra Nath | Technical Architect | Bench | Still in Organization | [13 empty] | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench
53 | Rajesh Kumar | Senior Technical Specialist | Bench | Still in Organization | [13 empty] | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench
54 | Naresh Ramineni | Senior Technical Specialist | Bench | Still in Organization | [13 empty] | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench
55 | Nagesh Thummalapally | Technical Specialist | Bench | Still in Organization | [13 empty] | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench
56 | Preeti Shrirame | Senior Software Engineer | Bench | Still in Organization | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench
57 | Deepak Patel | Senior Technical Specialist | Bench | Still in Organization | [22 empty] | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench
58 | Sreedhar Busetty | Senior Software Engineer | Bench | Still in Organization | [22 empty] | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench
59 | E Sri Aditya | Senior Software Engineer | Bench | Still in Organization | [22 empty] | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench
60 | Paramesh Sana | Senior Software Engineer | Bench | Still in Organization | [22 empty] | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench | Bench
Section D : Employees from partner ecosystem who has left the organisation in this period | Section D : Employees from partner ecosystem who has left the organisation in this period | Section D : Employees from partner ecosystem who has left the organisation in this period | Section D : Employees from partner ecosystem who has left the organisation in this period | Section D : Employees from partner ecosystem who has left the organisation in this period | Section D : Employees from partner ecosystem who has left the organisation in this period | Section D : Employees from partner ecosystem who has left the organisation in this period | Section D : Employees from partner ecosystem who has left the organisation in this period | Section D : Employees from partner ecosystem who has left the organisation in this period | Section D : Employees from partner ecosystem who has left the organisation in this period | Section D : Employees from partner ecosystem who has left the organisation in this period | Section D : Employees from partner ecosystem who has left the organisation in this period | Section D : Employees from partner ecosystem who has left the organisation in this period | Section D : Employees from partner ecosystem who has left the organisation in this period | Section D : Employees from partner ecosystem who has left the organisation in this period | Section D : Employees from partner ecosystem who has left the organisation in this period | Section D : Employees from partner ecosystem who has left the organisation in this period | Section D : Employees from partner ecosystem who has left the organisation in this period | Section D : Employees from partner ecosystem who has left the organisation in this period | Section D : Employees from partner ecosystem who has left the organisation in this period | Section D : Employees from partner ecosystem who has left the organisation in this period | Section D : Employees from partner ecosystem who has left the organisation in this period | Section D : Employees from partner ecosystem who has left the organisation in this period | Section D : Employees from partner ecosystem who has left the organisation in this period | Section D : Employees from partner ecosystem who has left the organisation in this period | Section D : Employees from partner ecosystem who has left the organisation in this period | Section D : Employees from partner ecosystem who has left the organisation in this period | Section D : Employees from partner ecosystem who has left the organisation in this period | Section D : Employees from partner ecosystem who has left the organisation in this period | Section D : Employees from partner ecosystem who has left the organisation in this period | Section D : Employees from partner ecosystem who has left the organisation in this period | Section D : Employees from partner ecosystem who has left the organisation in this period | Section D : Employees from partner ecosystem who has left the organisation in this period | Section D : Employees from partner ecosystem who has left the organisation in this period | Section D : Employees from partner ecosystem who has left the organisation in this period | Section D : Employees from partner ecosystem who has left the organisation in this period | Section D : Employees from partner ecosystem who has left the organisation in this period | Section D : Employees from partner ecosystem who has left the organisation in this period | Section D : Employees from partner ecosystem who has left the organisation in this period | Section D : Employees from partner ecosystem who has left the organisation in this period | Section D : Employees from partner ecosystem who has left the organisation in this period | Section D : Employees from partner ecosystem who has left the organisation in this period | Section D : Employees from partner ecosystem who has left the organisation in this period | Section D : Employees from partner ecosystem who has left the organisation in this period | Section D : Employees from partner ecosystem who has left the organisation in this period | Section D : Employees from partner ecosystem who has left the organisation in this period | Section D : Employees from partner ecosystem who has left the organisation in this period | Section D : Employees from partner ecosystem who has left the organisation in this period | Section D : Employees from partner ecosystem who has left the organisation in this period | Section D : Employees from partner ecosystem who has left the organisation in this period | Section D : Employees from partner ecosystem who has left the organisation in this period | Section D : Employees from partner ecosystem who has left the organisation in this period | Section D : Employees from partner ecosystem who has left the organisation in this period | Section D : Employees from partner ecosystem who has left the organisation in this period | Section D : Employees from partner ecosystem who has left the organisation in this period | Section D : Employees from partner ecosystem who has left the organisation in this period
61 | Medasani Vamsee Krishna | Senior Software Engineer | Non Billable | 17/11/2021 | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance | Reliance

## Bench Report
Roles | April |  | May |  | June |  | July |  | August |  | September |  | October |  | November |  | December |  | January |  | February |  | March
| Actual | Normalised Bench | Actual | Normalised Bench | Actual | Normalised Bench | Actual | Normalised Bench | Actual | Normalised Bench | Actual | Normalised Bench | Actual | Normalised Bench | Actual | Normalised Bench | Actual | Normalised Bench | Actual | Normalised Bench | Actual | Normalised Bench | Actual | Normalised Bench
Software Engg | 5.32 | NaN | 4.00 | NaN | 3.23 | NaN | 3.09 | NaN | 4.00 | NaN | 0.73 | NaN | 0.00 | NaN | 10.68 | NaN | 13.43 | NaN | 15.00 | NaN | 15.00 | NaN | 15.00 | NaN
Sen.Software Engg | 4.86 | NaN | 3.10 | NaN | 3.00 | NaN | 3.09 | NaN | 3.00 | NaN | 3.00 | NaN | 3.00 | NaN | 6.41 | NaN | 7.83 | NaN | 9.00 | NaN | 9.00 | NaN | 9.00 | NaN
Technical Specialist | 1.95 | NaN | 0.00 | NaN | 0.00 | NaN | 0.18 | NaN | 2.45 | NaN | 1.55 | NaN | 3.00 | NaN | 9.68 | NaN | 11.22 | NaN | 12.00 | NaN | 12.00 | NaN | 12.00 | NaN
Sen.Technical Specialist | 1.14 | NaN | 1.00 | NaN | 1.00 | NaN | 1.00 | NaN | 1.00 | NaN | 1.00 | NaN | 1.00 | NaN | 3.86 | NaN | 4.00 | NaN | 4.00 | NaN | 4.00 | NaN | 4.00 | NaN
Technical Architect | 2.82 | NaN | 2.00 | NaN | 0.68 | NaN | 0.09 | NaN | 0.00 | NaN | 0.18 | NaN | 1.00 | NaN | 8.68 | NaN | 9.00 | NaN | 10.00 | NaN | 10.00 | NaN | 10.00 | NaN
Sen.Technical Architect | 0.14 | NaN | 0.00 | NaN | 0.00 | NaN | 0.00 | NaN | 0.00 | NaN | 0.00 | NaN | 0.00 | NaN | 0.95 | NaN | 1.61 | NaN | 3.00 | NaN | 3.00 | NaN | 3.00 | NaN
Princ.Technical Architect | 1.27 | NaN | 1.00 | NaN | 1.00 | NaN | 1.00 | NaN | 1.00 | NaN | 1.41 | NaN | 2.00 | NaN | 2.00 | NaN | 2.00 | NaN | 2.00 | NaN | 2.00 | NaN | 2.00 | NaN
Asso.Princ.Technical Architect | 0.14 | NaN | 0.00 | NaN | 0.77 | NaN | 0.14 | NaN | 0.00 | NaN | 0.18 | NaN | 1.00 | NaN | 1.95 | NaN | 2.00 | NaN | 2.00 | NaN | 2.00 | NaN | 2.00 | NaN
Total | 17.64 | NaN | 11.10 | NaN | 9.68 | NaN | 8.59 | NaN | 11.45 | NaN | 8.05 | NaN | 11.00 | NaN | 44.23 | NaN | 51.09 | NaN | 57.00 | NaN | 57.00 | NaN | 57.00 | NaN
Simple Average | null% | null% | null% | null% | null% | null% | null% | null% | null% | null% | null% | null% | null% | null% | null% | null% | null% | null% | null% | null% | null% | null% | null% | null%

## Mom-23-11-2021
Minutes Of Meetings
[5 empty] | Date | 23/11/2021
Participants
ashish.modi@avekshaa.com
rachit.raj@avekshaa.com
ram.singh@avekshaa.com
rajinder.gandotra@avekshaa.com
vinayak.shinde@avekshaa.com
rishi.ranjan@avekshaa.com
Point Discussed |  | This is the test Mom for update 202
Point Agreed/Action Items |  | Task Details | Responsible | Status | Completion Date | Remarks
23/11/2021
| 1 | Axis Bank : Engage with Axis Bank to get into L1 and L2 support. | Ram Singh, Rachit Raj, Digendra Singh | Pending | 27/11/2021 | This will need continous engagement. Plan to share the success story from TCL and HDFC Bank
| 2 | Axis Bank : Keep the information restricted to need to know basis with the customer. We do not need to share the how part of the recommendation | Rachit Raj, Ram Singh, Rajinder Gandotra | WIP | 27/11/2021 | Teams have been instructed to keep the recommendations restrictive to the solution rather than the approach. This is being followed
| 3 | Axis Bank : If working beyond normal working hours, we shall bill the client at 1.5X. | Rachit Raj, Ram Singh | Done | 27/11/2021 | This will need to be discussed with Axis Bank
| 4 | Task 1 | Rachit Raj | TBD | 10/12/2021 | Test
| 5 | Axis Bank : Clearly call out that Avekshaa will not be providing any training to Axis Bank/partners for solving issues coming to the PM team 1 | Rachit Raj, Ram Singh, Rajinder Gandotra | NA | 23/11/2021 | The person concerned has been moved out to some other task. There is no pressure from Axis Bank